## Overview
SendCleared — Customer Growth Plan
2 hrs/day · 8-week build-out · Freelancer + Agency acquisition
Plan start date | 2026-08-27
Plan length | 8 weeks (40 working days)
Daily time budget | 120 minutes
Phase plan
Phase | Weeks | Focus | Primary goal
Phase 1 | Weeks 1-2 | Foundation: approval-led LP, beta agency recruiting, analytics setup | 10 beta agencies onboarded, tracking live
Phase 2 | Weeks 3-4 | Community presence, SEO content, first case studies | 3 SEO posts live, 2 testimonials, organic signups begin
Phase 3 | Weeks 5-6 | Public pricing launch, directory listings, Product Hunt | Stripe live, first paying customers
Phase 4 | Weeks 7-8 | Scale content + outreach, partnerships, retro | Compounding organic traffic, plan next 8 weeks
Weekly rhythm (Mon-Fri)
Day | Category | Purpose
Monday | SEO / Content | Keyword research, drafting, publishing, on-page optimisation
Tuesday | Cold email | Building target lists, outreach batches, follow-ups
Wednesday | Community / answering questions | Reddit, Slack/Discord, Indie Hackers, X — genuine engagement, no pitching
Thursday | Listings / partnerships | Directories, partner programmes, Product Hunt, affiliate/cross-promo
Friday | Metrics + admin | Weekly review, testimonials, case studies, pricing/ops tasks
Progress summary (auto-updates from Daily Plan tab)
Metric | Value
Total tasks | 94
Tasks done | #VALUE!
Tasks in progress | #VALUE!
Tasks not started | #VALUE!
% complete | 0%

## Daily Playbook
SendCleared — Daily Outreach Playbook ¦ 1 Hour / Day
Goal: 15-20 LinkedIn actions + 1 content piece + 3-5 community touches per day → drive approval-link signups (freelancers + agencies)
Day | Date | Focus | LinkedIn Actions (15-20) | Content | Community (Reddit/Indie Hackers) | Email Follow-ups | Done? | Notes
WEEK 1 — Foundation: warm up profile, join communities
1 | 2026-08-27 | Optimise Upwork/LinkedIn profile + join 5 relevant communities | Join r/emailmarketing, r/agency, r/freelance, Indie Hackers, 1 relevant Slack/Discord. Update headline to mention SendCleared. | Write LinkedIn post: 'The £47 email mistake no one talks about' — soft intro, no hard sell | Introduce yourself in each community — no pitching, just context | — | ☐
2 | 2026-08-28 | Agency target list — batch 1 | Send 10 connection requests to agency owners/account managers (Klaviyo/Mailchimp partner directories). Personalise each. | — | Bookmark 5 recent threads about email QA/client approval to answer next week | — | ☐
3 | 2026-08-29 | Freelancer audience — Upwork/LinkedIn | Send 10 connection requests to freelance email marketers. Comment on 5 posts in freelance/agency groups. | Write LinkedIn post: 'Why looks approved isn't the same as is approved' — educational | Answer 1 community question about client sign-off on campaigns | — | ☐
4 | 2026-08-30 | Direct outreach — agencies (batch 2) | Send 10 personalised LinkedIn DMs to agency owners. Introduce yourself, ask about their approval process — DON'T pitch yet. 10 new connections. | — | Post in a community: genuine tip on catching QA mistakes before send | — | ☐
5 | 2026-08-31 | Follow-up day + freelancer batch 2 | Follow up Day 1-2 connections who haven't replied. Send 10 connection requests to freelance email marketers. | Write community answer: 'Best way to get client sign-off on email campaigns' — detailed, link SendCleared | — | — | ☐
WEEK 2 — Warm leads: first real pitches
6 | 2026-09-01 | Pitch agencies who connected last week | DM agencies from Day 4 who accepted: 'Happy to give you free access to try — QA + client approval in one link.' 10 new connections. | LinkedIn post: 'How agencies lose client trust in one broken subject line' — soft mention | Answer community question: 'How to prove a client approved an email campaign' | Follow up Day 1 DMs (4 days later) | ☐
7 | 2026-09-02 | Community — mixed engagement | Comment helpfully on 10 posts in r/emailmarketing / r/agency. Send 10 connection requests to freelancers. | — | Post in r/agency: brief mention of SendCleared in context of client approval | Follow up Day 2 connections | ☐
8 | 2026-09-03 | Freelancer outreach (batch 1) | DM 10 freelancers connected last week: 'Ever have a client dispute what they approved? SendCleared gives you a clean audit trail.' | LinkedIn post: 'The pre-send checklist top email agencies actually use' — practical, shareable | — | Follow up Day 3 DMs | ☐
9 | 2026-09-04 | Agency operations DMs | DM 10 agency owners: 'If client sign-off is still happening over Slack/email, SendCleared gives you one link per campaign. Happy to set you up free.' | — | Answer community question about approval workflows for agencies | Follow up Day 4 connections | ☐
10 | 2026-09-05 | Weekly review + follow-up sweep | Review all week's DMs. Send follow-up #2 to non-responders. 10 new connections. | Write blog post outline: 'What I learned reviewing 500 client emails before they went out' | Check community replies, respond to comments | Follow up Day 5 DMs | ☐
WEEK 3 — Scale: community authority + agency batch 2
11 | 2026-09-06 | Community blitz — QA and approval pain points | 10 new connections (mix freelancers + agency owners). Comment on 5 LinkedIn posts. | LinkedIn post: 'The audit trail your client is quietly expecting' — high value | Answer 3 community questions today, spaced 2 hours apart | Follow up Week 1 non-responders (10-day follow-up) | ☐
12 | 2026-09-07 | Indie Hackers — soft entry | Find and join 2-3 relevant Slack/Discord communities for agencies. Lurk before posting. 10 LinkedIn connections. | — | Post on Indie Hackers: build-in-public update, share early numbers | Follow up Week 1 DMs (10 days) | ☐
13 | 2026-09-08 | Freelancer/agency audience mix | DM 10 freelancers or agency ops leads: 'If client sign-off is still 'reply to approve', SendCleared gives a clean, timestamped record. Free trial.' 10 connections. | LinkedIn post: 'The 3 questions every client should ask before hitting send' | Answer community question: 'best way to get client approval for email campaigns' | Follow up Week 2 batch 1 | ☐
14 | 2026-09-09 | Multi-ESP / agency push | DM 10 agencies managing multiple ESPs (Klaviyo + Mailchimp + ActiveCampaign). Mention ESP-agnostic approval hub angle. 10 connections. | — | Post in relevant agency-ops community | Follow up Week 2 batch 2 | ☐
15 | 2026-09-10 | Testimonial + referral ask | DM/email any users who've tried SendCleared: ask for a quick testimonial + 'know any other agencies who'd find this useful?' 10 new connections. | LinkedIn post: share a real use case or result (anonymise if needed) | — | Follow up Week 2 non-responders | ☐
WEEK 4 — Content compound: posts + answers building authority
16 | 2026-09-11 | Community group posting — max reach | Post SendCleared-relevant content inside 3 relevant groups/communities (not just your feed). 10 connections. Reply to all comments on previous posts. | LinkedIn post: 'Why your ESP can't catch these 5 mistakes (but your process should)' — technical, high share value | Answer community question: 'how to catch email QA mistakes before sending' | Follow up Week 3 batch 1 | ☐
17 | 2026-09-12 | Cold email outreach — agencies (batch 1) | Find 20 agency websites via Google/directories. Email 20 agencies: introduce SendCleared, offer free trial. Keep it personal. | — | Post in agency community: client approval workflow tips | Follow up Week 3 DMs | ☐
18 | 2026-09-13 | Community — first soft post in new group | In a new agency-ops Slack/Discord: post a genuinely helpful tip about client approval. No hard sell. Mention SendCleared naturally if asked. 10 LinkedIn connections. | LinkedIn post: 'Why I built SendCleared' — founder story, drives trust and shares | — | Follow up Week 3 non-responders | ☐
19 | 2026-09-14 | ESP partner channel | Search LinkedIn for Klaviyo/Mailchimp partners and bookkeeping-style agency directories. DM 10. 10 connections. | — | Answer community question: 'best tool for multi-client email approval' | Follow up cold email batch from Day 17 (2 days) | ☐
20 | 2026-09-15 | Mid-programme review | Audit: how many signups so far? Which channel converting best? Adjust Week 5-6 focus toward the winner. 10 connections. | Write LinkedIn post: data/results post — '20 days of outreach, here's what I learned' | Review and respond to all community comments | Follow up all outstanding DMs | ☐
WEEK 5 — Double down on what's working
21 | 2026-09-16 | Agency email batch 2 | Send 20 more cold emails to agencies. Refine subject line based on Week 4 open rates. 10 connections. | LinkedIn post: 'The email QA checklist we use before every send' | Answer 2 community questions | Follow up Week 4 email batch (4 days) | ☐
22 | 2026-09-17 | Community mega-answer day | Find the 5 highest-traffic threads about email QA/client approval. Write the single best answer on each. 10 connections. | — | Post detailed 'from draft to approved' workflow post | Follow up Week 4 DM batch | ☐
23 | 2026-09-18 | LinkedIn carousel | Create a carousel: '5 steps to a bulletproof email approval workflow' — highest engagement format on LinkedIn. 10 connections. | LinkedIn carousel: approval workflow step-by-step | — | Follow up Week 3 long-tail non-responders | ☐
24 | 2026-09-19 | Partnership outreach — ESP/agency directories | Email 5 directories or agency-focused newsletters about a guest post or listing. 10 LinkedIn connections. | Draft guest post pitch for agency-ops blogs | Answer community question: 'best email QA tool for agencies' | Follow up Week 5 email batch (3 days) | ☐
25 | 2026-09-20 | Referral programme soft launch | DM existing users: 'For every agency you refer who signs up, I'll extend your plan free for a month.' 10 connections. | LinkedIn post: announcing referral offer | — | Sweep all outstanding follow-ups | ☐
WEEK 6 — Harvest + system lock-in
26 | 2026-09-21 | Convert warm leads — final push | Revisit every lead who engaged but didn't convert. Personalised DM: 'Still happy to set you up with extended free access — takes 2 minutes.' 10 connections. | LinkedIn post: 'Month 1 in numbers — what outreach actually drives signups' | Respond to all outstanding community comments | Final follow-up to all email campaigns | ☐
27 | 2026-09-22 | Final agency email batch | Send 20 final agency emails. Refine to best-performing subject line from Weeks 4-5. 10 connections. | — | Post recap in agency community with SendCleared mention | Follow up Week 6 batch 1 (1 day) | ☐
28 | 2026-09-23 | Lock in top channels for Month 2 | Identify top 2 channels by signup conversion. Write a simple SOP for each so you can systematise Month 2. 10 connections. | LinkedIn post: 'Here's exactly how I'm growing SendCleared with 1 hour a day' | — | Follow up all Week 6 DMs | ☐
29 | 2026-09-24 | Testimonial and case study push | Email every trial user. Ask for: (a) testimonial, (b) upgrade to paid, (c) referral. 10 connections. | Write LinkedIn post: user testimonial (with permission) | Answer 2 community questions | Follow up Week 6 email batch | ☐
30 | 2026-09-25 | Month 1 review + Month 2 plan | Compile: total connections, DMs sent, emails sent, community answers, signups. Set Month 2 targets. 10 connections. | Write Month 2 outreach plan (1 page doc) | Final community posts — thank the communities | Send final follow-up to any remaining warm leads | ☐

## Lead Tracker
SendCleared — Lead Tracker ¦ Log every person you contact
Status colour key: 🟢 Converted 🟡 Warm 🔴 Cold / No reply ⚪ New
ID | Name | Title / Role | Company | Segment | Country | Channel | Contact Date | Touch 1 (Date) | Touch 2 (Date) | Touch 3 (Date) | Status | Trial? | Paid? | Notes / Next Action
1 | Jordan Blake | Founder | Blake Digital | Agency | UK | LinkedIn DM | 27 Jul 26 | 27 Jul 26 | 31 Jul 26 |  | Warm | Yes | No | EXAMPLE ROW — replace with a real contact. Trial started, follow up in 5 days re: pricing.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## DM Templates
SendCleared — Message Templates (Copy, Personalise, Send)
LINKEDIN CONNECTION REQUEST
Freelancer segment | Hi [Name], I built SendCleared — a tool that runs a pre-send QA check and gets client sign-off on every email campaign, whatever ESP you use. Would love to connect with other email freelancers.
Agency segment | Hi [Name], I run SendCleared, which gives agencies a single link for client approval on every campaign — plus a QA check before it goes out. Would love to connect given the client-facing work you do.
FIRST DM — AFTER CONNECTING
Freelancer — Touch 1 | Hi [Name], thanks for connecting! Quick question — when a client signs off on a campaign, is that a proper approval, or just a 'looks good' reply? We built SendCleared specifically to give freelancers a clean, timestamped approval link. Happy to set you up with free access if useful.
Agency — Touch 1 | Hi [Name], thanks for connecting. Do your clients ever dispute what they actually approved on a send? SendCleared gives you one link per campaign — QA checked, client approved, fully logged. Happy to give you free access to try it.
FOLLOW-UP DMs
Touch 2 (Day +4) — No reply yet | Hi [Name], just following up — happy to give you free access to try SendCleared, no strings attached. Takes 2 minutes to set up your first client. Would that be useful?
Touch 3 (Day +10) — Final nudge | Hi [Name], last message from me on this — if client approval or pre-send QA is ever a headache, SendCleared is there. Here's the link: sendcleared.com. Happy to answer any questions anytime.
COLD EMAIL — AGENCIES
Subject line options | Option A: 'A single approval link for every campaign, any ESP' Option B: 'Stop chasing client sign-off over Slack' Option C: 'Pre-send QA + client approval, in one step'
Email body | Hi [Name], I'm the founder of SendCleared (sendcleared.com) — it runs a QA check on every email campaign and gets client sign-off through a single branded link, regardless of which ESP you use. I thought this might save your account managers the back-and-forth of chasing approval over Slack or email threads. There's a 14 day free trial available — no credit card, no commitment. Would that be useful? Best, [Your name]
COMMUNITY ANSWER TEMPLATE (Reddit / Indie Hackers / Slack)
Structure for any 'how do you get client sign-off / catch mistakes before sending' thread | Para 1: Acknowledge the pain — verbal or Slack-based approval doesn't hold up when a client disputes what they actually saw. Para 2: Cover the common workarounds briefly (screenshot + reply-all, shared docs) and their limits. Para 3: Mention tools including SendCleared — 'I've been using SendCleared (sendcleared.com), which generates a branded approval link with a timestamped record — handles the QA and the sign-off in one step.' Para 4: Practical tip about keeping a record even without a tool (e.g. a dated screenshot at minimum). Keep it 150-250 words. Don't make the SendCleared mention the focus — make the answer genuinely helpful.
SendCleared — Outreach Emails & Follow-Up Sequence
Copy, personalise the [bracketed] fields, and send. Timing shown is days after the previous email if no reply.
| FREELANCER SEGMENT | AGENCY SEGMENT
EMAIL 1 — INITIAL OUTREACH (Day 0)
Subject line options | A) "Quick one re: client sign-off on your campaigns" B) "Ever had a client dispute what they approved?" C) "A cleaner way to get client sign-off" | A) "A single approval link for every campaign, any ESP" B) "Stop chasing client sign-off over Slack" C) "Pre-send QA + client approval, in one step"
Body | Hi [Name], I noticed you do email marketing for clients — quick question: when a client signs off on a campaign, is that a proper approval, or more of a "looks good" reply over email or Slack? We built SendCleared (sendcleared.com) to give freelancers a clean, timestamped approval link instead — it also runs a quick 14 point QA check before the client even sees it (broken links, missing alt text, personalization errors). a free trial is available to try on your next campaign — no card, no commitment. Would that be useful? Best, [Your name] | Hi [Name], I'm the founder of SendCleared (sendcleared.com) — it runs a QA check on every email campaign and gets client sign-off through a single branded link, regardless of which ESP you use. I thought this might save your account managers the back-and-forth of chasing approval over Slack or email threads — especially if you're running campaigns across more than one ESP. I'd love to give your agency free access to try it — no credit card, no commitment. Would that be useful? Happy to jump on a 10-minute call too. Best, [Your name]
EMAIL 2 — FOLLOW-UP 1 (Day +4, if no reply)
Subject line | Re: Quick one re: client sign-off on your campaigns | Re: A single approval link for every campaign, any ESP
Body | Hi [Name], Just floating this back up in case it got buried. Free access to SendCleared.com is still open if useful — takes about 2 minutes to set up your first client, and works with whatever ESP you're using. I attached a quick one pager for you. No pressure either way — let me know if it's not a fit right now. Best, [Your name] | Hi [Name], Following up on my note below — happy to set your agency up with free access to SendCleared, no strings attached. Takes a few minutes to add your first client. Let me know if it's useful, or if now's just not the right time. Best, [Your name]
EMAIL 3 — FOLLOW-UP 2 / FINAL NUDGE (Day +10, if no reply)
Subject line | Last note from me on this | One last thought, then I'll leave it there
Body | Hi [Name], Last message from me on this one — if pre-send QA or client sign-off is ever a headache, SendCleared is there whenever it's useful: sendcleared.com. Happy to answer any questions any time, no follow-up needed from you. Best, [Your name] | Hi [Name], Last note from me — if client approval or juggling QA across ESPs ever becomes a pain point, SendCleared is there: sendcleared.com. Free to try whenever it's useful. All the best with the agency's work either way. [Your name]
EMAIL 4 — TRIAL / WARM LEAD NUDGE (send once someone has started a free trial but hasn't sent a campaign)
Subject line | Anything I can help set up? | Anything I can help set up?
Body | Hi [Name], Saw you signed up for SendCleared — happy to help get your first client's inbox address connected if that'd save you time, or answer any questions about how the QA report works. Just reply here and I'll sort it. Best, [Your name] | Hi [Name], Saw your team signed up for SendCleared — happy to help onboard your first couple of clients, or walk through the QA report and approval flow with your account managers if useful. Just reply here and I'll get it set up. Best, [Your name]
EMAIL 5 — REFERRAL ASK (send to active/paying users)
Subject line | Quick favour, if you don't mind | Quick favour, if you don't mind
Body | Hi [Name], Glad SendCleared's been useful. Quick ask — know any other freelancers who deal with the same client-approval headache? For every referral who signs up, I'll extend your plan free for a month. No worries at all if not — just thought I'd ask. Best, [Your name] | Hi [Name], Glad SendCleared's been working well for your team. Quick ask — know any other agencies dealing with the same client sign-off chaos? For every referral who signs up, I'll extend your plan free for a month. No worries if not — just thought I'd ask. Best, [Your name]

## LinkedIn Requests
SendCleared — LinkedIn Requests
Agency segment — profile URL | Date sent | Follow up | Freelancer segment — profile URL | Date sent
https://www.linkedin.com/in/example-agency-owner/ | EXAMPLE — paste real profile URLs below |  | https://www.linkedin.com/in/example-freelancer/ | EXAMPLE — paste real profile URLs below
LinkedIn search — agencies |  |  | LinkedIn search — freelancers
https://www.linkedin.com/search/results/people/?keywords=email%20marketing%20agency%20owner |  |  | https://www.linkedin.com/search/results/people/?keywords=freelance%20email%20marketer

## Weekly Scoreboard
SendCleared — Weekly Outreach Scoreboard
Metric | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | TOTAL | Target
LinkedIn Connections Sent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350
LinkedIn Connections Accepted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
LinkedIn DMs Sent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150
DMs Replied | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
Cold Emails Sent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
Email Replies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Community Answers Posted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
LinkedIn Posts Published | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
Trial Sign-ups (from outreach) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
Paid Conversions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
⚠️ Blue cells are weekly actuals — fill in each Friday. Targets assume ~1 hour/day outreach. If a channel is converting well, shift volume toward it and adjust next week's targets.

## Channel Strategy
SendCleared — Channel Strategy & Rules of Engagement
Channel | Time Budget | Weekly Volume | What Works | What to Avoid | When to Escalate | Tool Needed?
LinkedIn DMs | 15 min/day | 10-15 DMs | Ultra-personal: name their ESP or a specific pain (client disputes, Slack chaos). Ask a question first — don't pitch in the first DM. | Generic copy-paste. Mentioning SendCleared in the connection request. Sending 3 follow-ups. | If >5 replies/week → increase volume | LinkedIn Sales Nav (Month 2 if budget allows)
LinkedIn Posts | 10 min/day | 1 post every 2 days | Educational content, practical checklists, founder story. QA-mistake and approval-accountability angles. | Pure product promotion. Too many hashtags. Posting and disappearing — reply to every comment. | If post gets >500 views → write a follow-up post on same topic | None — just LinkedIn native
LinkedIn Groups | 5 min/day | 5-10 comments | Comment helpfully on others' posts before promoting. Join conversations — don't start with a pitch. | Dropping links without context. Self-promotion in groups that ban it. | If group member messages you → fast-track to DM flow | —
Cold Email | 10 min/day | 20 emails/day (4 days/week) | Short, personal, clear offer (free trial). Subject line specific to their ESP or client-approval pain. | Long emails. Attachments. BCC blasts. Following up more than twice. | If reply rate >10% → double the volume | Gmail tracker (Streak or Mailtrack — free tier fine)
Reddit / Indie Hackers | 10 min/day | 1-2 answers/day | Write the best answer on the thread. 150-250 words. SendCleared mention natural, not leading. | Thin answers. Dropping just a link. Answering questions with 0 engagement. | If answer gets traction → update it and share on LinkedIn | —
Agency/ESP Slack & Discord communities | 5 min/day (lurk first) | 1 genuine post/week max | Answer questions helpfully for 1-2 weeks before mentioning any tool. Build trust first. | Spamming groups. Posting without reading group rules. Mentioning SendCleared in first post. | If someone DMs asking for recommendations → send them to SendCleared directly | —
Directories / Listings | 10 min/day (batched) | 2-3 submissions/week | Target 'best tools for agencies' roundups and ESP partner directories (Klaviyo, Mailchimp). | Low-quality directories with no real traffic. Paying for placement before validating referral quality. | If a listing sends real signups → prioritise similar ones | —

## Linked in Content Plan
LinkedIn Content Plan — 10 articles
Scheduled into the Daily Plan tab (Monday content slots) across weeks 1-8
# | Title | Pillar | Angle / hook | Scheduled week | Status
1 | The £47 email mistake no one talks about | QA / mistakes | A single unresolved merge tag or broken link, multiplied across a whole list — the real cost of skipping QA. | Week 1 | Not started
2 | Why 'looks approved' isn't the same as 'is approved' | Approval / accountability | The gap between a client skimming a Slack message and a client actually reviewing the send. | Week 2 | Not started
3 | The 3 questions every client should ask before hitting send | Approval / accountability | A short, shareable checklist clients can use — positions the agency as the one who already asks these. | Week 3 | Not started
4 | What I learned reviewing 500 client emails before they went out | QA / mistakes | Pattern-based lessons from common QA failures — broken personalization, missing alt text, bad preview text. | Week 3 | Not started
5 | The hidden cost of 'just reply-all to approve' | Approval / accountability | Why informal approval chains create disputes later, and what a real audit trail looks like. | Week 4 | Not started
6 | How agencies lose client trust in one broken subject line | Agency operations / trust | A single visible mistake and its outsized effect on a client relationship. | Week 5 | Not started
7 | The pre-send checklist top email agencies actually use | QA / mistakes | A practical, tactical checklist post — highly shareable, doubles as a lead magnet. | Week 6 | Not started
8 | Why your ESP can't catch these 5 mistakes (but your process should) | QA / mistakes | ESPs check deliverability, not content accuracy — the gap that pre-send QA fills. | Week 6 | Not started
9 | The audit trail your client is quietly expecting | Approval / accountability | Clients increasingly expect proof of sign-off, especially after a mistake elsewhere burns them. | Week 7 | Not started
10 | From draft to approved: what a modern email workflow actually looks like | Agency operations / trust | End-to-end narrative post — draft, QA, client approval link, send. Good for late-plan, when case studies exist. | Week 8 | Not started

## Community Questions
SendCleared — Community Question Bank (Reddit / Indie Hackers / Slack)
Template answers for the question types you'll typically see — adapt with the real thread's wording before posting.
Question type | Draft answer (adapt before posting) | Date answered
How do you actually get client sign-off on an email campaign before it sends? | Most teams end up with sign-off buried in a Slack thread or a 'looks good' reply — which works fine until a client disputes what they actually saw. A cleaner approach is a dedicated approval link: the client reviews the exact rendered email, approves or requests changes, and that action gets a timestamp and a name attached. I've been using SendCleared (sendcleared.com) for this — it also runs a QA check before the client even sees it, so obvious mistakes (broken merge tags, missing alt text) get caught first. Whatever tool you use, the key is having something more durable than a chat message as your record.
What's the best way to catch mistakes in an email before it goes out to the whole list? | A mix of manual checklist and automated checks works best. Manually: check the subject line and preview text render correctly, click every link, check the unsubscribe and physical address are present. Automated: tools like SendCleared (sendcleared.com) run this as a pre-send QA pass — checking merge tags, broken links, missing alt text, and spam triggers — which catches the stuff that's easy to miss under deadline pressure. Either way, build the check into your process as a required step, not an optional one.
We manage multiple clients across different ESPs (Klaviyo, Mailchimp, etc.) — is there a way to centralise approvals? | This is a common pain once you're past 2-3 clients on different platforms — each ESP has its own (or no) approval mechanism, so you end up with a different process per client. A platform-agnostic approval layer sits on top of whichever ESP the client uses, so your team has one consistent workflow regardless of the backend. SendCleared (sendcleared.com) works this way — it ingests the campaign via a forwarded test send, so it doesn't care which ESP you're on. Worth looking at if the fragmentation is slowing your team down.
How do freelancers prove to clients that an email was reviewed properly before sending? | A dated screenshot of your own checklist is the bare minimum, but it's not much of a record if a client pushes back later. A better approach is a client-facing approval step — they see the actual rendered email and click approve themselves, which creates a natural audit trail without extra admin on your end. I use SendCleared (sendcleared.com) for this — it also gives the client a branded page rather than a random link, which reads as more professional than a Slack message.
Common QA Failures & Disaster Stories - Quora - Target email marketing category - will need to keep broad
"What is the worst email marketing mistake you've ever made or seen?"
"How do you prevent sending an email with broken links or bad merge tags ({{first_name}})?"
"Why do my HTML emails look broken in Outlook or Apple Mail?"
Pre-Send Process & Checklists
"What is your pre-launch checklist before hitting 'Send' on an email campaign?"
"How do email marketers perform QA on automated lifecycle flows (Klaviyo, HubSpot, etc.)?"
"What is the best way to double-check email render and formatting across different clients?"
Tooling & Alternatives
"Are there any good alternative tools to Litmus or Email on Acid for email QA testing?"
"What are the best automated tools to catch email bugs before broadcast?"
"How do you test dark mode rendering for HTML email newsletters?"
Strategy to Plug SendCleared on Quora
Provide a High-Value Framework First: Don't just post a sales link. Give a structured 4-point manual checklist (e.g., checking subject lines/preheaders, testing live fallback tags, rendering on mobile/dark mode, verifying preview texts).
Introduce the "Automated Solution": Explain that doing manual checks across every broadcast or automation update takes 15–20 minutes and still leaves room for human error.
Soft Pitch: "To speed this up and catch things like broken dynamic tags or broken layouts automatically, tools like SendCleared run these pre-flight checks instantly before you send."

## SEO Content Plan
SEO Content Plan — 3 pillars, 3 cornerstones, 12 cluster posts
Each cornerstone is the pillar's cornerstone page; cluster posts link back to it. Ordered roughly TOFU → BOFU within each pillar.
# | Pillar | Type | Title | Target keyword | Search intent | Funnel stage | Scheduled | Status
1 | Pillar 1 — QA / mistakes | Cornerstone | The Email QA Checklist for Agencies and Freelancers | email QA checklist | Informational | Cornerstone | Week 2-3 | Not started
2 | Pillar 1 — QA / mistakes | Cluster | The £47 email mistake no one talks about | email personalization errors | Informational | TOFU | Week 7-8 | Not started
3 | Pillar 1 — QA / mistakes | Cluster | Why your ESP can't catch these 5 mistakes | email QA vs ESP testing | Informational | TOFU | Month 2 | Not scheduled
4 | Pillar 1 — QA / mistakes | Cluster | What I learned reviewing 500 client emails before they went out | pre-send email checklist | Informational | TOFU/MOFU | Month 2 | Not scheduled
5 | Pillar 1 — QA / mistakes | Cluster | How to catch broken merge tags before sending | merge tag errors email | Informational, specific | MOFU | Month 2 | Not scheduled
6 | Pillar 2 — Approval / accountability | Cornerstone | How to Get Client Sign-Off on Email Campaigns (Without the Slack Chaos) | client approval workflow email | Informational | Cornerstone | Week 3-4 | Not started
7 | Pillar 2 — Approval / accountability | Cluster | The 3 questions every client should ask before hitting send | client email sign off checklist | Informational, shareable | TOFU | Month 2 | Not scheduled
8 | Pillar 2 — Approval / accountability | Cluster | Why "looks approved" isn't the same as "is approved" | client approval workflow email | Informational | MOFU | Month 2 | Not scheduled
9 | Pillar 2 — Approval / accountability | Cluster | The hidden cost of "just reply-all to approve" | email approval process for agencies | Informational | MOFU | Month 2 | Not scheduled
10 | Pillar 2 — Approval / accountability | Cluster | The audit trail your client is quietly expecting | email approval audit trail | Commercial-adjacent | MOFU/BOFU | Month 3 | Not scheduled
11 | Pillar 3 — Agency operations / trust | Cornerstone | Running a Professional Email QA & Approval Process as an Agency | email agency workflow | Informational | Cornerstone | Week 5-6 | Not started
12 | Pillar 3 — Agency operations / trust | Cluster | How agencies lose client trust in one broken subject line | email mistakes client trust | Informational | TOFU | Month 2 | Not scheduled
13 | Pillar 3 — Agency operations / trust | Cluster | The pre-send checklist top email agencies actually use | email agency workflow | Informational | MOFU | Month 2 | Not scheduled
14 | Pillar 3 — Agency operations / trust | Cluster | One approval hub for every ESP, not five logins | multi-ESP client approval | Commercial-adjacent | BOFU | Month 3 | Not scheduled
15 | Pillar 3 — Agency operations / trust | Cluster | From draft to approved: what a modern email workflow looks like | email approval software | Commercial | BOFU | Month 3 | Not scheduled
16 | Pillar 1 — QA / mistakes | Cluster | How to Send a Test Email Your Client Can Actually Review | send test email (320/mo, difficulty 28) | Informational, high-intent | TOFU/MOFU | Not scheduled | Not started
17 | Pillar 1 — QA / mistakes | Cluster | Why Emails Land in Spam: A Pre-Send Deliverability Checklist | how to stop emails going to spam (210/mo); spamhaus (1,600/mo) | Informational | TOFU | Not scheduled | Not started
18 | Pillar 1 — QA / mistakes | Cluster | The Anatomy of a Broken Email Link (and How to Catch It Before Sending) | html email link / link in html email (320/mo, difficulty 29-33) | Informational, specific | MOFU | Not scheduled | Not started
NEW — Comparison Pages (zero competitor coverage found in keyword-gap analysis)
19 | Comparison / competitive | Comparison | Litmus Alternative for Agencies and Freelancers | litmus alternative (no reported volume in gap data — untapped) | Commercial, high-intent | BOFU | Not scheduled | Not started
20 | Comparison / competitive | Comparison | Email on Acid vs SendCleared: Which One Do You Actually Need? | email on acid alternative (no reported volume — untapped) | Commercial, comparison | BOFU | Not scheduled | Not started
21 | Comparison / competitive | Comparison | Why Generic Proofing Tools (Ziflow, Filestage, Ashore) Don't Work for Email | email approval software (no direct competitor overlap found) | Commercial, comparison | BOFU | Not scheduled | Not started
22 | Comparison / competitive | Comparison | The Best Client Approval Tool for Email Marketers (2026) | email approval software / client sign off tool | Commercial | BOFU | Not scheduled | Not started
Rows 1-4 (orange) are scheduled into the Daily Plan tab, weeks 1-8. Rows 5-18 are Month 2-3 backlog. Rows 19-22 (blue) are new comparison pages, added from the Litmus/Mailtrap/Email on Acid keyword-gap analysis — none of the three competitors rank for approval, sign-off, proofing, or freelance terms, and no 'alternative'/'vs' comparison content exists yet for this category.

## Community Posts
SendCleared — Community Posts Log
Post URL | Date | Outcome / Notes
https://www.reddit.com/r/agency/comments/example_post/ | 27 Jul 26 | EXAMPLE — 40 upvotes, 2 DMs from agency owners, 1 signup

## Directory Listings
Tier 1 — high-authority, worth the effort (submit in week 1)
Directory | Why it matters
Product Hunt | The single biggest traffic spike opportunity; treat launch day as an event, not a passive listing
G2 | List under "Email Testing Software" — the same category Litmus and Email on Acid sit in, so you're in front of people actively comparing
Capterra | Same category-matching logic as G2; Gartner-owned, high buyer trust
GetApp | Also Gartner-family — same listing content works across all three with minor edits
AlternativeTo | Directly relevant given your comparison-page strategy — list Litmus and Email on Acid as the tools SendCleared is an alternative to
Crunchbase | Less about traffic, more about legitimacy signal for anyone researching the company
SaaSHub | Good DR, accepts "alternative to X" framing directly
Tier 2 — fast, free, low-effort dofollow listings (batch these, 3–5/day)
Indie Hackers — also worth being active in, not just listed; your build-in-public content already fits this audience
BetaList — less relevant now you're past pre-launch, but still worth a listing for backlink value
StackShare — more dev-tool-oriented, lower priority but easy
F6S — startup-focused, decent authority
Smol Launch / Launching Next / DevHunt — modern, curated, genuinely free dofollow links; good ROI for the time cost
Avoid: mass-submission/auto-approval services (PRLog, EzineArticles-style, or anyone offering "300 directories in a day") — these are flagged as actively harmful to domain authority now, not just low-value.
Tier 3 — niche fit for your specific audience
AppSumo — lifetime-deal marketplace; strong fit since your audience (freelancers, small agencies) is exactly who browses there, but worth thinking through the trade-off: LTD revenue is a one-time hit that can undercut your recurring MRR model. Worth a deliberate decision, not a default yes.
Klaviyo App Marketplace / Integrations directory and Mailchimp equivalent — these are the highest-intent placements possible given your actual ICP, but they typically require a formal technical integration/certification process, not just a listing form. Flag this as a "pursue once you have engineering time," not a quick win.
Show HN (Hacker News) — not a directory, but a free "Show HN: SendCleared" post at launch or a major update can be genuinely high-leverage if it lands — technical/founder audience, thousands of eyes if it catches on. Zero cost to try.

## Contacts
Profile | Type | Agency | Name | Emailed (Linkedin) | Connect Request | Second Send
https://www.linkedin.com/in/zoelacey/ | Freelancer |  | Zoe Lacey |  | 05.09.26
https://www.linkedin.com/in/wiktoria-wilczy%C5%84ska-3850ba162/ | Freelancer |  | Wiktoria Wilczyńska | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/wassif-a-a63a8330/ | Freelancer |  | Wassif A
https://www.linkedin.com/in/victoriaapg1/ | Freelancer |  | Victoria ap Gwynedd | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/vernesacutuk/ | Freelancer |  | Vernesa Ćutuk | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/towfiqul-alam/ | Freelancer |  | Towfiqul Alam | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/tehseen-arbab-0b15aa1ab/ | Freelancer |  | Tehseen Arbab | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/sylvester-swea-b2a1b87b/ | Freelancer |  | Sylvester Swea | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/shaun-reynolds-email-marketing/ | Freelancer |  | Shaun Reynolds
https://www.linkedin.com/in/sean-duffy-crm-email-marketing/ | Freelancer |  | Sean Duffy |  | 05.09.26 | 16.09.26
https://www.linkedin.com/in/sarah-brereton-b0199935/ | Freelancer |  | Sarah Brereton |  | 05.09.26 | 16.09.26
https://www.linkedin.com/in/pireland1/ | Freelancer |  | Phil Ireland | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/oviakpojotor/ | Freelancer |  | Ovi Akpojotor | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/nils-g-08583421a/ | Freelancer |  | Nils Goldingers
https://www.linkedin.com/in/neha-gupta-0a20bb147/ | Freelancer |  | Neha Gupta | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/natashasweiss/ | Freelancer |  | Natasha Weiss | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/naomimdavies/ | Freelancer |  | Naomi Davies |  | 05.09.26 | 16.09.26
https://www.linkedin.com/in/imuhammadmuneeb/ | Freelancer |  | Muhammad Muneeb | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/mohitkumar7/ | Freelancer |  | Mohit Kumar | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/milica-botha-42770b164/ | Freelancer |  | Milica Botha | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/margaret-ward-/ | Freelancer |  | Margaret Ward | 05.09.26
https://www.linkedin.com/in/luc-de-bruin-9813a695/ | Freelancer |  | Luc de Bruin | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/louise-rebecca-thomas/ | Freelancer |  | Louise Rebecca Thomas | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/kathpay/ | Freelancer |  | Kath Pay | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/kate-reeves-0b068a3a/ | Freelancer |  | Kate Reeves
https://www.linkedin.com/in/kehammond1/ | Freelancer |  | Kate Hammond | 05.09.26 |  | 16.09.26
https://www.linkedin.com/in/karantibdewal/ | Freelancer |  | Karan Tibdewal | 07.09.26 |  | No Connected
https://www.linkedin.com/in/judithjornetgomez-salesforce/ | Freelancer |  | Judith Jornet Gomez | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/jeannejennings/ | Freelancer |  | Jeanne Jennings | 07.09.26 |  | No Connected
https://www.linkedin.com/in/israaa/ | Freelancer |  | Israa A. | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/holinessgodrey/ | Freelancer |  | Holiness Godfrey | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/haseeb-ahmedd/ | Freelancer |  | Haseeb Ahmed | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/hsrivastava0205/ | Freelancer |  | Harshita Srivastava | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/hannahspicer/ | Freelancer |  | Hannah Spicer |  |  | 16.09.26
https://www.linkedin.com/in/hamza-bukhari-953b3b257/ | Freelancer |  | Hamza Bukhari | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/dikshikaroutray/ | Freelancer |  | Dikshika Routray | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/diego-de-sevilla-acosta-2b9304284/ | Freelancer |  | Diego De Sevilla Acosta | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/dhikrullah-abimbola-07062a191/ | Freelancer |  | Dhikrullah Abimbola | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/dantabaran/ | Agency |  | Dan Tabaran | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/chloe-mcleod-16841968/ | Freelancer |  | Chloe McLeod | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/chirag-kotadiya-622058140/ | Freelancer |  | Chirag Kotadiya | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/carmenemailmarketing/ | Freelancer |  | Carmen Lee | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/queenofcrm/ | Freelancer |  | Beth O'Malley |  |  | 16.09.26
https://www.linkedin.com/in/astra-tsangaris/ | Freelancer |  | Astra Tsangaris | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/antony-newbold-hazebrooke-copywriting/ | Freelancer |  | Antony Newbold | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/anthony-hilary-715036232/ | Freelancer |  | Anthony Hilary | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/akingkiwi/ | Freelancer |  | Andrew King | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/allanheo/ | Freelancer |  | Allan Heo | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/ali-hassan-6aa1571ba/ | Freelancer |  | Ali Hassan | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/abdulmomen1/ | Freelancer |  | ABDUL MOMEN | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/aaronmagalong/ | Freelancer |  | Aaron Magalong | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/peter-nwede-483597259/ | Freelancer |  | Peter Nwede | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/sonaton-emaildeveloper/ | Freelancer |  | Sonaton Mondol | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/tais-tomazoni-997720ab/ | Freelancer |  | Tais Tomazoni | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/tom-nguyen-411911371/ | Freelancer |  | Tom Nguyen | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/tomseebold/ | Freelancer |  | Tom Seebold | 07.09.26 |  | 16.09.26
https://www.linkedin.com/in/janagardiner/ | Freelancer |  | Jana Gardiner | 07.09.26
https://www.linkedin.com/in/annettforcier/ | Freelancer |  | Annett Forcier | 07.09.26 |  | 23.09.26
https://www.linkedin.com/in/harringtonben/ | Freelancer |  | Ben Harrington | 07.09.26 |  | 23.09.26
https://www.linkedin.com/in/jaspervanlaethem/ | Freelancer |  | Jasper Van Laethem | 07.09.26 |  | 23.09.26
https://www.linkedin.com/in/lauren-barrett-708166163/ | Freelancer |  | Lauren Barrett | 07.09.26
https://www.linkedin.com/in/jayde-laws-929311128/ | Freelancer |  | Jayde Laws | 07.09.26 |  | No Connected
https://www.linkedin.com/in/george-lindh/ | Freelancer |  | George Lindh | 07.09.26 |  | 23.09.26
https://www.linkedin.com/in/claudia-preuss-a4b310151/ | Freelancer |  | Cloudie Preuss | 07.09.26 |  | 23.09.26
https://www.linkedin.com/in/kevin-parady/ | Freelancer |  | Kevin Parady | 15.09.26 |  | No Connected
https://www.linkedin.com/in/lucyovers/ | Freelancer |  | Lucy Overs | 15.09.26 |  | No Connected
https://www.linkedin.com/in/belyndamurray/ | Freelancer |  | Belynda (Belle) Murray | 15.09.26 |  | No Connected
https://www.linkedin.com/in/plamen-tonev/ | Freelancer |  | Plamen Tonev | 15.09.26 |  | No Connected
https://www.linkedin.com/in/tizian-bauer/ | Freelancer |  | Tizian Bauer | 15.09.26 |  | No Connected
https://www.linkedin.com/in/anwesha-singh-6996ab153/ | Freelancer |  | Anwesha Singh | 15.09.26 |  | 23.09.26
https://www.linkedin.com/in/jeremyklaviyo/ | Freelancer |  | Jeremy Vincent R. Dela Cruz | 15.09.26
https://www.linkedin.com/in/jocelyn-abel-85a903149/ | Freelancer |  | Jocelyn Abel | 15.09.26
https://www.linkedin.com/in/rakic-milos/ | Freelancer |  | Milos Rakic | 15.09.26
https://www.linkedin.com/in/letitia-tita-b45712100/ | Freelancer |  | Letitia Tita | 15.09.26
https://www.linkedin.com/in/alen-capelja/ | Freelancer |  | Alen Capelja | 15.09.26
https://www.linkedin.com/in/christina-vasiliadou/ | Freelancer |  | Christina Vasiliadou | 15.09.26
https://www.linkedin.com/in/david-jim/ | Freelancer |  | David Jimenez | 15.09.26
https://www.linkedin.com/in/andreea-maria-micl%C4%83u%C8%99-8b1474b8/ | Freelancer |  | Andreea-Maria Miclaus | 15.09.26
https://www.linkedin.com/in/lauraserbest/ | Freelancer |  | Laura S. | 15.09.26
https://www.linkedin.com/in/peyman-karimian/ | Freelancer |  | Peyman Karimian | 15.09.26
https://www.linkedin.com/in/biljana-dukleska-a1b48132/ | Freelancer |  | Biljana Dukleska | 15.09.26
https://www.linkedin.com/in/idris-farjad-622846197/ | Freelancer |  | Idris Farjad | 15.09.26
https://www.linkedin.com/in/robson-esteves/?locale=en | Freelancer |  | Robson Esteves Daniel | 15.09.26
https://www.linkedin.com/in/areeba-ahmed-1535b6180/ | Freelancer |  | Areeba Ahmed | 15.09.26
https://www.linkedin.com/in/laura-vaakanainen/ | Freelancer |  | Laura Vaakanainen | 15.09.26
https://www.linkedin.com/in/emilythrockmorton/ | Freelancer |  | Emily Throckmorton | 15.09.26
https://www.linkedin.com/in/danielghiroltean/ | Freelancer |  | Daniel Ghiroltean | 15.09.26
https://www.linkedin.com/in/markokoprivica/ | Freelancer |  | Marko Koprivica | 15.09.26
https://www.linkedin.com/in/sumant-goyal-3b957030b/ | Freelancer |  | Sumant Goyal | 15.09.26
https://www.linkedin.com/in/aneela-rana-22120a31b/ | Freelancer |  | Aneela Rana | 15.09.26
https://www.linkedin.com/in/tierraexum/ | Freelancer |  | Tierra Grosman | 15.09.26
https://www.linkedin.com/in/leon-matthew-989354206/ | Freelancer |  | Leon Matthew | 15.09.26
https://www.linkedin.com/in/valeriarobles24/ | Agency |  | Valeria Robles
https://www.linkedin.com/in/kristi-treder-7289965/ | Agency |  | Kristi Treder
https://www.linkedin.com/in/nikoloz-saralidze-2314b8154/ | Client |  | Nikoloz Saralidze
https://www.linkedin.com/in/victor-bizuett-6a954991/?locale=en | Freelancer |  | Victor Bizuett |  | 22.09.26
https://www.linkedin.com/in/denaskulinicius/ | Client |  | Denas Kuliničius
https://www.linkedin.com/in/taylorlumpkin/ | Agency |  | Taylor Lumpkin
https://www.linkedin.com/in/klaviyo-expert/ | Freelancer |  | Ryan Turner |  | 22.09.26
https://www.linkedin.com/in/rr-chris-lawbuary/ | Freelancer |  | Chris Lawbuary |  | 22.09.26
https://www.linkedin.com/in/gnegrin/ | Freelancer |  | Gabriel Negrín |  | 22.09.26
https://www.linkedin.com/in/barbarabsantos/ | Agency |  | Bárbara Santos
Profile | Type | Agency | Name | Emailed (Linkedin) | Connect Request | Second Send
https://www.linkedin.com/in/williamconsult/ | Client |  | William Ma
https://www.linkedin.com/in/rachel-j-79296b129/ | Client |  | Rachel Johnson
https://www.linkedin.com/in/olivia-tildesley-278aa182/ | Client |  | Olivia Tildesley
https://www.linkedin.com/in/aranchagomezarranz/ | Client |  | Arancha Gómez
https://www.linkedin.com/in/yurii-zuban/ | Agency |  | Yurii Zuban | 07.09.26
https://www.linkedin.com/in/peter-kim-1a31a7244/ | Agency |  | Peter Kim | 07.09.26
https://www.linkedin.com/in/narmin-fraint-b762a4210/ | Agency |  | Narmin Fraint | 07.09.26
https://www.linkedin.com/in/michelle-young-36468a20/ | Agency |  | Michelle Young | 07.09.26
https://www.linkedin.com/in/margaret-ward-/ | Agency |  | Margaret Ward | 07.09.26
https://www.linkedin.com/in/lana-williams-9b4442b8/ | Agency |  | Lana Williams | 07.09.26
https://www.linkedin.com/in/jack-squire/ | Agency |  | Jack Squire
https://www.linkedin.com/in/emmahwm/ | Agency |  | Emma Thao Nguyen | 07.09.26
https://www.linkedin.com/in/elrize-erasmus-43883a1a5/ | Agency |  | Elrize Erasmus | 07.09.26
https://www.linkedin.com/in/pablo-mart%C3%ADnez-emailmarketing-ecommerce/ | Agency |  | Pablo Martínez | 07.09.26
https://www.linkedin.com/in/rhysalanharris/ | Agency |  | Rhys Harris | 07.09.26
https://www.linkedin.com/in/danielwilcox32/ | Agency |  | Daniel Wilcox | 07.09.26
https://www.linkedin.com/in/olimpia-valentina-chiriacescu/ | Agency |  | Olimpia Valentina Chiriacescu | 07.09.26
https://www.linkedin.com/in/abril-herrera-dorna/ | Agency | Perfit Email Marketing | Abril Herrera Dorna |  | 22.09.26
https://www.linkedin.com/in/mayra-altamirano-perfit/ | Agency | Perfit Email Marketing | Mayra Altamirano |  | 22.09.26
https://www.linkedin.com/in/fernandezwalter/?locale=en | Agency | Perfit Email Marketing | Walter Fernández |  | 22.09.26
https://www.linkedin.com/in/nataliia-hushkovska/ | Agency | Selzy ¦ Email Marketing | Nataliia Hushkovska |  | 22.09.26
https://www.linkedin.com/in/alexkachalov/ | Agency | Selzy ¦ Email Marketing | Alexey Kachalov |  | 22.09.26
https://www.linkedin.com/in/christine-hombrink/ | Agency | Robly Email Marketing | Christine (Allen) Hombrink |  | 22.09.26
https://www.linkedin.com/in/betty-p-carpenter-503806154/ | Agency | Email Marketing Solutions | Betty P. Carpenter |  | 22.09.26
https://www.linkedin.com/in/souhail-hadouch-226a22161/ | Agency | Email Marketing Solutions | Souhail Hadouch |  | 22.09.26
https://www.linkedin.com/in/rotney-jacob-743744108/ | Agency | Email Marketing Solutions | Rotney Jacob |  | 22.09.26
https://www.linkedin.com/in/jeremy-fleming-311b81198/ | Agency | Insendra | Jeremy Fleming |  | 22.09.26
https://www.linkedin.com/in/xiaohuiw/ | Agency | Essence of Email | Xiaohui "X" Wang |  | 22.09.26
https://www.linkedin.com/in/philip-mbwaya-ab593758/ | Agency | Essence of Email | Philip Mbwaya |  | 22.09.26
https://www.linkedin.com/in/dabhi-bhumil-6427a01b7/ | Agency | Essence of Email | Dabhi Bhumil |  | 22.09.26
https://www.linkedin.com/in/daniel-anzalone/ | Agency | Firedrum | Daniel Anzalone |  | 22.09.26
https://www.linkedin.com/in/kevin-troendle-b3782a2b/ | Agency | Firedrum | Kevin Troendle |  | 22.09.26
https://www.linkedin.com/in/adel-gouida-1aa4a61b8/ | Agency | The Email Marketers | Adel Gouida |  | 22.09.26
https://www.linkedin.com/in/stevanovic-nenad/ | Agency | The Email Marketers | Nenad Stevanović |  | 22.09.26
https://www.linkedin.com/in/patricia-cabrera-768202179/ | Agency | Email Allstars | Patricia Cabrera |  | 22.09.26
https://www.linkedin.com/in/sriramgangs/ | Agency | Email Industries | Sriram G |  | 22.09.26
https://www.linkedin.com/in/rafsan-jamil-625842379/ | Agency | Email Industries | Rafsan Jamil |  | 22.09.26
https://www.linkedin.com/in/rushabh-shah-8a8537143/ | Agency | Mavlers | Rushabh Shah |  | 22.09.26
https://www.linkedin.com/in/tiernan-corcoran-6a65b4373/ | Agency | Social Scout Email Marketing | Tiernan Corcoran |  | 22.09.26
https://www.linkedin.com/in/monicanaidoo/ | Agency | Social Scout Email Marketing | Mónica Naidoo |  | 22.09.26
https://www.linkedin.com/in/feryhdz/ | Agency | Social Scout Email Marketing | Maria Fernanda (Fery) Hernandez Diaz |  | 22.09.26
https://www.linkedin.com/in/mariamarafante/ | Agency | Social Scout Email Marketing | Maria M |  | 22.09.26
https://www.linkedin.com/in/mayur-prajapati-4a7b86256/ | Agency | RankFast ¦ Search Marketing Company | Mayur Prajapati |  | 22.09.26
https://www.linkedin.com/in/christina-dali-7a5539210/ | Agency | CANZ Marketing | Christina Dali |  | 22.09.26
https://www.linkedin.com/in/abby-bruke-95a273210/ | Agency | CANZ Marketing | Abby Bruke |  | 22.09.26
https://www.linkedin.com/in/ecom-michael-galvin/ | Agency | No Limit Email | Michael Galvin |  | 22.09.26
https://www.linkedin.com/in/tatiana-garcia-posada/ | Agency | No Limit Email | Tatiana García Posada |  | 22.09.26
https://www.linkedin.com/in/raquelherrerahdez/?locale=en | Agency | Benchmark Email | Raquel Herrera Hernández |  | 22.09.26
https://www.linkedin.com/in/jessica-lunk-39391017/ | Agency | Benchmark Email | Jessica Lunk |  | 22.09.26
https://www.linkedin.com/in/daniela-canob/ | Agency | Benchmark Email | Daniela Cano |  | 22.09.26
https://www.linkedin.com/in/surender-kumar8/ | Agency | Benchmark Email | Surender Kumar |  | 22.09.26
https://www.linkedin.com/in/anna-rose-elkins-93baa011b/ | Agency | BAD Marketing | Anna Rose Elkins |  | 22.09.26
https://www.linkedin.com/in/kelsey-carstens/ | Agency | BAD Marketing | Kelsey Carstens |  | 22.09.26
https://www.linkedin.com/in/peter-gonglach/ | Agency | BAD Marketing | Peter Gonglach |  | 22.09.26
https://www.linkedin.com/in/emily-godwin-84a57b74/ | Agency | RepuVue Marketing Agency | Emily Godwin |  | 22.09.26
https://www.linkedin.com/in/angelaspeziale/ | Agency | RepuVue Marketing Agency | Angela Speziale |  | N/A
https://www.linkedin.com/in/ghulam-akbar-6273b3341/ | Agency | Alpha Co. Marketing & Media | Ghulam Akbar |  | 22.09.26
https://www.linkedin.com/in/mat%C3%ADas-nahuel-rizzi-del-r%C3%ADo-b749aa18b/?locale=en | Agency | Alpha Co. Marketing & Media | Matías Nahuel Rizzi del Río |  | 22.09.26
https://www.linkedin.com/in/ekeh-paul-2288a3215/ | Agency | Less Is Moore Email Marketing | Ekeh Paul |  | 22.09.26
https://www.linkedin.com/in/chloejpg/ | Agency | Less Is Moore Email Marketing | Chloe L |  | 22.09.26
https://www.linkedin.com/in/saad-chaudhry-/ | Agency | Progressive Marketing | Saad Chaudhr |  | 22.09.26
https://www.linkedin.com/in/manzar2000/ | Agency | Progressive Marketing | Syed Manzar Hussain |  | 22.09.26
https://www.linkedin.com/company/digitalmarketingcompanyagency/
https://www.linkedin.com/company/repuvue/
https://www.linkedin.com/company/aspen-marketing-services/
https://www.linkedin.com/company/alpha-co-marketing-media/
https://www.linkedin.com/company/marlomarketing/
https://www.linkedin.com/company/hiredigitalco/
https://www.linkedin.com/company/mavlers/
https://www.linkedin.com/company/vml/
https://www.linkedin.com/company/digitalzoneb2b/
https://www.linkedin.com/company/npdigital/
https://www.linkedin.com/company/email-love/
https://www.linkedin.com/company/elliot-digital/
https://www.linkedin.com/company/flowium/
https://www.linkedin.com/company/optimailonline/
https://www.linkedin.com/company/email-agency/
https://www.linkedin.com/company/chronosagency/
https://www.linkedin.com/company/email-data-group/
https://www.linkedin.com/company/b2i-digital/
https://www.linkedin.com/company/b2i-digital/
https://www.linkedin.com/company/outcomes-rocket/
https://www.linkedin.com/company/retention-dot-com/
https://www.linkedin.com/company/brickmarketing/
https://www.linkedin.com/company/hawkemedia/
https://www.linkedin.com/company/risequadagency/
https://www.linkedin.com/company/valasys-media/
https://www.linkedin.com/company/apprise-marketing-services-ams/
https://www.linkedin.com/company/lilosocial/